## Slide 1: Project Cost Management

## Slide 2: The Importance of Project Cost Management
IT projects have a poor track record for meeting budget goals
A cost overrun is the additional percentage or dollar amount by which actual costs exceed estimates
A 2011 Harvard Business Review study reported an average cost overrun of 27 percent. The most important finding was the discovery of a large number of gigantic overages or “black swans”

## Slide 3: What is Cost and Project Cost Management?
Cost is a resource sacrificed or foregone to achieve a specific objective or something given up in exchange
Costs are usually measured in monetary units like dollars
Project cost management includes the processes required to ensure that the project is completed within an approved budget

## Slide 4: Project Cost Management Processes
Planning cost management :determining the policies, procedures, and documentation that will be used for planning, executing, and controlling project cost.
Estimating costs: developing an approximation or estimate of the costs of the resources needed to complete a project
Determining the budget: allocating the overall cost estimate to individual work items to establish a baseline for measuring performance
Controlling costs: controlling changes to the project budget

## Slide 5: Figure 7-1. Project Cost Management Summary
  Planning
    Process
      Plan cost management
    Outputs
      Cost management pan
    Process
      Estimate costs
    Outputs
      Activity costs estimates
      basis of estimates
      project documents updates
    Process
      Determine budget
    Outputs
      Cost baseline
      Project funding requirements
      Project documents updates
  Monitoring and Controlling
    Process
      Control costs
    Outputs
      Work performance information
      Cost forecasts
      Change requests
      Project management plan updates
      Project documents updates
      Organizational process assets updates
Project Finish

## Slide 6: Types of Costs and Benefits
Tangible costs or benefits are those costs or benefits that an organization can easily measure in dollars
Intangible costs or benefits are costs or benefits that are difficult to measure in monetary terms
Direct costs are costs that can be directly related to producing the products and services of the project
Indirect costs are costs that are not directly related to the products or services of the project, but are indirectly related to performing the project
Sunk cost is money that has been spent in the past; when deciding what projects to invest in or continue, you should not include sunk costs

## Slide 7: More Basic Principles of Cost Management
Learning curve theory states that when many items are produced repetitively, the unit cost of those items decreases in a regular pattern as more units are produced
Reserves are dollars included in a cost estimate to mitigate cost risk by allowing for future situations that are difficult to predict
  Contingency reserves allow for future situations that may be partially planned for (sometimes called known unknowns) and are included in the project cost baseline
  Management reserves allow for future situations that are unpredictable (sometimes called unknown unknowns

## Slide 8: Planning Cost Management
The project team uses expert judgment, analytical techniques, and meetings to develop the cost management plan
A cost management plan includes:
  Level of accuracy and units of measure
  Organizational procedure links
  Control thresholds
  Rules of performance measurement
  Reporting formats
  Process descriptions

## Slide 9: Estimating Costs
Project managers must take cost estimates seriously if they want to complete projects within budget constraints
It’s important to know the types of cost estimates, how to prepare cost estimates, and typical problems associated with IT cost estimates

## Slide 10: Table 7-1. Types of Cost Estimates
TYPE OF ESTIMATE | WHEN DONE | WHY DON’T | HOW ACCURATE
Rough order of magnitude (ROM) | Very early in the project life cycle. | Provides estimate of cost for selection decisions | -50% to +100%
Budgetary | During project planning or when scope is clearer | Puts dollars in the budget plans | -10% to +25%
Definitive | Once project design and scope are well defined (execution planning phase) | Provides details for purchases, estimates actual costs | -5% to+10%

## Slide 11: Cost Estimation Tools and Techniques
Basic tools and techniques for cost estimates:
  Analogous or top-down estimates: use the actual cost of a previous, similar project as the basis for estimating the cost of the current project
  Bottom-up estimates: involve estimating individual work items or activities and summing them to get a project total
  Parametric modeling uses project characteristics (parameters) in a mathematical model to estimate project costs

## Slide 12: Typical Problems with IT Cost Estimates
Estimates are done too quickly
People lack estimating experience
Human beings are biased toward underestimation
Management desires accuracy

## Slide 13: Sample Cost Estimate
See the text for a detailed example of creating a cost estimate for the Surveyor Pro project described in the opening case
Before creating an estimate, know what it will be used for, gather as much information as possible, and clarify the ground rules and assumptions for the estimate
If possible, estimate costs by major WBS categories
Create a cost model to make it easy to make changes to and document the estimate

## Slide 14: Figure 7-2. Surveyor Pro Project Cost Estimate
Surveyor Pro Project Cost Estimate October 5
Empty cell | # Units/Hrs. | Cost/Unit/Hr. | Subtotals | WBS Level 2 Totals | % of Total
WBS Items | Empty cell | Empty cell | Empty cell | Empty cell | Empty cell
1. Project Management | Empty cell | Empty cell | Empty cell | $306,300 | 20%
Project manager | 960 | $100 | $96,000 | Empty cell | Empty cell
Project team members | 1920 | $75 | $144,000 | Empty cell | Empty cell
Contractors (10% of software development and testing) | Empty cell | Empty cell | $66,300 | Empty cell | Empty cell
2. Hardware | Empty cell | Empty cell | Empty cell | $76,000 | 5%
2.1 Handheld devices | 100 | $600 | $60,000 | Empty cell | Empty cell
2.2 Servers | 4 | $4,000 | $16,000 | Empty cell | Empty cell
3. Software | Empty cell | Empty cell | Empty cell | $614,000 | 40%
3.1 Licensed software | 100 | $200 | $20,000 | Empty cell | Empty cell
3.2 Software development* | Empty cell | Empty cell | $594,000 | Empty cell | Empty cell
4. Testing (10% of total hardware and software costs) | Empty cell | Empty cell | $69,000 | $69,000 | 5%
5. Training and Support | Empty cell | Empty cell | Empty cell | $202,400 | 13%
Trainee cost | 100 | $500 | $50,000 | Empty cell | Empty cell
Travel cost | 12 | $700 | $8,400 | Empty cell | Empty cell
Project team members | 1920 | $75 | $144,000 | Empty cell | Empty cell
6. Reserves (20% of total estimate) | Empty cell | Empty cell | $253,540 | $253,540 | 17%
Total project cost estimate | Empty cell | Empty cell | Empty cell | $1,521,240 | Empty cell
*See software development estimate

## Slide 15: Figure 7-3. Surveyor Pro Software Development Estimate
1. Labor Estimate | # Units/Hrs. | Cost/Unit/Hr. | Subtotals | Calculations
Contractor labor estimate | 3000 | $150 | $450,000 | 3000*150
Project team member estimate | 1920 | $75 | $144,000 | 1920*75
Total labor estimate | Empty cell | Empty cell | $594,000 | Sum above two values
Empty cell | Empty cell | Empty cell | Empty cell | Empty cell
2. Function point estimate | Quantity | Conversion Factor | Function Points | Calculations
External inputs | 10 | 4 | 40 | 10*4
External interface files | 3 | 7 | 21 | 3*7
External outputs | 4 | 5 | 20 | 4*5
External queries | 6 | 4 | 24 | 6*4
Logical internal tables | 7 | 10 | 70 | 7*10
Total function points | Empty cell | Empty cell | 175 | Sum above function point values
Java 2 language equivalency value | Empty cell | Empty cell | 46 | Assumed value from reference
Source lines of code (SLOC) estimate | Empty cell | Empty cell | 8,050 | 175*46
ProductivityxKSLOC^Penalty (in months) | Empty cell | Empty cell | 29.28 | 3.13*8.05^1.072 (see reference)
Total labor hours (27 hours/function point)* | Empty cell | Empty cell | 4,725 | 27*175
Cost/labor hour ($120/hour) | Empty cell | Empty cell | $120 | Assumed value from budget expert
Total function point estimate | Empty cell | Empty cell | $567.000 | 4,725*120
*Based on historical data
© Cengage Learning 2016

## Slide 16: Determining the Budget
Cost budgeting involves allocating the project cost estimate to individual work items over time
The WBS is a required input to the cost budgeting process since it defines the work items
Important goal is to produce a cost baseline
  a time-phased budget that project managers use to measure and monitor cost performance

## Slide 17: Controlling Costs
Project cost control includes
  Monitoring cost performance
  Ensuring that only appropriate project changes are included in a revised cost baseline
  Informing project stakeholders of authorized changes to the project that will affect costs
Many organizations around the globe have problems with cost control

## Slide 18: Project Portfolio Management
Many organizations collect and control an entire suite of projects or investments as one set of interrelated activities in a portfolio
Five levels for project portfolio management
  Put all your projects in one database
  Prioritize the projects in your database
  Divide your projects into two or three budgets based on type of investment
  Automate the repository
  Apply modern portfolio theory, including risk-return tools that map project risk on a curve

## Slide 19: Summary
Project cost management is a traditionally weak area of IT projects, and project managers must work to improve their ability to deliver projects within approved budgets
Main processes include
  Plan cost management
  Estimate costs
  Determine the budget
  Control costs