## Slide 1: Project Initiation & Planning

## Slide 2: Project Charter & Statement of Work
The project charter is a document that outlines the primary project objectives and assigns roles and responsibilities.
The project charter helps the involved project managers and the stakeholders understand what the given project is supposed to accomplish.
It defines the project's scope, offers deadlines and milestones, and provides information on identified risks and the budget.
This document remains with you throughout the project's life cycle. You’ll be referring to it throughout, whether at meetings or to assist with scope management. The charter acts as a roadmap.
A project manager typically writes the project charter, however, it requires collaboration with different stakeholders to be a success

## Slide 3: Project Charter & Statement of Work
Statement of Work
A detailed contract-style document that describes exactly what work will be performed and how deliverables will be produced.
SoW is a purely technical document prepared by the vendor, outlining the technical solution and the services the vendor is going to build or provide in a project.
SoW is used externally by the company.
Differences between Project Charter and SoW
Aspect | Project Charter | Statement of Work (SOW)
Level of Detail | High-level, summary | Very detailed, technical, and contractual
Prepared by | Project sponsor/initiator | Client (buyer) or jointly with the vendor
Focus | Why the project is done, who is involved | What will be delivered, how, when, and under what conditions
Formality | Internal project authorization | Often contractual (can be legally binding)
Timing | Created at project initiation | Created before execution or contracting

## Slide 4: How to Write a Project Charter: Key Elements of a Project Charter
The project charter typically documents the following parts of the project:
  State the Project Information
  Project objectives and constraints
  Key stakeholders
  Risks identified
  Benefits of the project
  General overview of the budget
  Success metrics

## Slide 5: State the Project Information
This first section in your project charter is where you’ll include your project’s general information, such as:
  Name,
  Description
  Project sponsor
  Project manager
  Team members, and
  Stakeholders

## Slide 6: Project objectives and constraints
Outline the main objectives of the project. These objectives should be SMART:
  Specific
  Measurable
  Achievable
  Realistic, and
  Time-bound.
Identify the constraints:
  Budget: Limited financial resources
  Time: Deadlines and milestones
  Resources: Availability of skilled team members, tools, or technology
  Stakeholder Requirements: Changing or conflicting expectations
  Scope Limitations: Boundaries of what is included/excluded
  Regulatory/Compliance Issues: Legal and policy constraints

## Slide 7: Project Timeline & Milestones
Define Start & End Dates
  Establish official project kickoff date
  Set project completion deadline
Identify Key Milestones
  Major deliverables and checkpoints
  Examples: Requirements finalized, Prototype completed,
  Testing phase start, Go-live date
Breakdown Activities
  Divide the project into phases and tasks
  Assign estimated durations for each task
Create a Timeline
  Use Gantt charts or milestone charts
  Show dependencies between tasks
Dynamic Tracking
  Input timeline into project management software (e.g., MS Project, Jira, Trello)
  Update progress in real-time to monitor delays and bottlenecks

## Slide 8: Key stakeholders
Identifying Stakeholders: Anyone who is affected by, involved in, or can influence the project’s success.
List All Stakeholders:
  Internal: Project sponsor, project manager, development team, testers
  External: Customers, vendors, regulators, end-users
Define Roles & Responsibilities:
  Sponsor: Provides funding & overall support
  Project Manager: Oversees execution
  Team Members: Deliver tasks & outputs
  End-users: Provide requirements & feedback
Identify Needs from Stakeholders:
  Approvals, resources, requirements, expertise, feedback
Maintain Contact Information:
  Emails, phone numbers, communication channels (Slack, Teams, etc.)

## Slide 9: Log Key Project Risks
  Types of Risks:
  Technical Risks: System failures, integration issues
  Resource Risks: Limited staff, skill shortages, budget cuts
  Schedule Risks: Delays, scope creep, unrealistic deadlines
  Stakeholder Risks: Changing requirements, low engagement
  External Risks: Regulatory changes, vendor delays, market shifts
Risk Management Plan :
  Identify: List potential risks early
  Analyze: Assess probability and impact
  Respond: Avoid, mitigate, transfer, or accept risk
  Monitor: Continuously track risks and update the plan

## Slide 10: Benefits of the project
Consider and describe how the project will positively impact:
  Stakeholders
  Customers.
  End users
Be as specific as possible, as it’s important to keep the benefits in mind as you work through the project to prioritize effectively

## Slide 11: General overview of the budget
According to PMI, Project management costs 7–11% of the total project budget
High-Level Financial Overview
Available Funds: Total approved budget
Anticipated Costs Breakdown:
    Project Management (7–11%) – planning, monitoring, reporting
    Human Resources – salaries, training, consultants
    Technology & Tools – software licenses, hardware
    Operations – facilities, utilities, travel, communication
    Quality Assurance & Testing – validation, audits
    Risk Reserves – contingency funds for unforeseen issues

## Slide 12: Success Metrics
  Success metrics provide measurable targets for project outcomes
  Support performance monitoring and evaluation
Key Performance Indicators (KPIs):
  On-time delivery of milestones
  Staying within budget limits
  Meeting quality standards (e.g., defect rates, compliance levels)
  Customer/end-user satisfaction levels
  Stakeholder engagement and approval
Other Metrics:
    Team productivity and efficiency
    Risk management effectiveness (resolved vs. open risks)
    ROI (Return on Investment) or the business value achieved

## Slide 13: Sample Project Charter for Website Development
Deliverables:
    Fully functional website with modern UI/UX
    Content migration from old website
    Documentation & training for content management
    Final project report
High-Level Timeline & Milestones:
    Requirements Gathering: Month 1
    Design & Prototyping: Month 1–2
    Development & CMS Setup: Month 2–3
    Testing & QA: Month 3
    Deployment & Training: Month 4
Estimated Budget:
Total: $40,000 (design, development, content migration, testing, training, contingency)
Project Title: University Website Redesign
Project Purpose:
Redesign and develop the university website to improve user experience, accessibility, and responsiveness, while modernizing content management for staff.
Project Objectives (SMART):
    Specific: Develop a responsive, accessible, and user-friendly website
    Measurable: Achieve 95% user satisfaction in usability surveys
    Achievable: Utilize existing IT team and CMS platform
    Relevant: Supports university branding and digital presence
    Time-bound: Complete redesign within 4 months
Scope:
  In Scope: Homepage redesign, faculty pages, news & events, student portal integration, content migration, responsive design
  Out of Scope: Third-party portal integration beyond the student portal, internal HR systems

## Slide 14: Sample Project Charter for Website Development (cont..)
Assumptions:
Content will be provided on time by department heads
Hosting and domain services will be maintained during project
Success Metrics:
  95% user satisfaction in usability surveys
  Completion of website within project timeline and budget
  Zero critical defects at deployment
  At least 90% content migrated correctly
  Positive stakeholder feedback post-launch
Approval Signatures:
Project Sponsor: _____________________
Project Manager: _____________________
Date: _____________________
Project Team Members & Roles:
    Project Manager: Web Project Lead – oversees execution, scheduling, and resources
    Lead Developer: Senior web developer – supervises coding and integration
    Front-end Developers: 2 members – build UI and responsive design
    Back-end Developers: 2 members – implement server-side functionality
    UI/UX Designer: 1 member – create design mockups and prototypes
    QA/Testers: 2 members – functional, performance, and accessibility testing
    Content Specialist: 1 member – content migration and review
    Support Staff: 1 member – documentation, training, and coordination
    End-users: Students, faculty, staff – provide feedback and accept deliverables
Constraints:
  Budget limited to $40,000
  Completion within 4 months
  Limited availability of senior web designers

## Slide 15: Quizzes
A vendor is contracted to supply and install solar panels for a university campus. The document includes site details, technical specifications of the panels, warranty information, and payment terms.
A new software project has just been approved. The sponsor has asked for a document that identifies the project manager, objectives, high-level scope, and success criteria. Which document is this?
Your team is preparing a contract with an external vendor. The vendor wants clear details on project deliverables, payment terms, schedule, and acceptance conditions. Which document is required?
A government agency is launching a new project to digitize land records. The project sponsor requests a document that states the project’s purpose, names the project manager, and lists the major stakeholders. Which document is required?
Before project execution, the steering committee wants to see a document that shows who the sponsor is, what problem the project will solve, and the estimated high-level budget.

## Slide 16: Assignment
Jira is a popular project management and issue-tracking tool. It is widely used in software development, especially in Agile environments, to plan, track, and manage projects efficiently.
Task 1: Explore Jira Basics
Task 2: Create a Sample Project
  Create a new project (Scrum or Kanban).
  Add at least 5 tasks/issues, assigning them to team members (can be fictional).
  Set priorities (High, Medium, Low) and due dates.
  Add descriptions for each task, defining acceptance criteria.
Task 3: Organize and Track Work
Create a sprint (if Scrum) or organize tasks on a Kanban board.
Move tasks through stages (To Do → In Progress → Done).
Monitor progress using Jira reports (Burndown chart, Sprint report, etc.).